## Title Page
RD.045 MoSCoW List |  | <Document Reference Number>
2019-11-07 18:43
OUM
RD.045 MoSCoW List
<Company Long Name>
<Subject>
| Author: | <Author>
| Creation Date: | 2010-01-01
| Last Updated: | 2010-01-01
| Document Ref: | <Document Reference Number>
| Version: | 0.1
Approvals
| Approver | Signature
<Approver 1>
<Approver 2>

## General Instructions
RD.045 MoSCoW List |  |  |  |  | <Document Reference Number>
2019-11-07 18:43
General Instructions
1 | Use this template to create a MoSCoW (Must have, Should Have, Could Have, or Won't Have) Requirements Work Product.
2 | Also consider using this template as a traceability matrix. Additional Sheets have been provided after the MoSCoW sheet that will facilitate the traceability of high level requirements to functional requirements, to business rules, to Service Oriented Architecture, to Test Cases, as appropriate for individual projects.
3 | This work product is meant to scale up or down; under some conditions, you may want to merge work products from other tasks into this one as additional sheets. In some situations, the project may be very large, in that case, it is recommended that an automated tool is used such as Oracle Enterprise Repository, rather than using this spreadsheet to produce your work product.
4 | Each individual worksheet contains instructions on how it should be used. See cells with comments as indicated by the red triangle in the upper right corner of the cell.
|  | Condition | Approach
|  | SOA Services may be managed within a middleware tool or within the enterprise repository | You should review the task RA.025 Identify Candidate Services. You may choose to combine the spreadsheet from the RA.025 into this workbook for smaller projects.
|  | Scrum Product backlog and Sprint Backlog are included in this workbook | Project Managers using a Scrum approach to project management will use the last two sheets of this workbook for the Product Backlog and Sprint Backlog. Please review the Using Scrum in OUM White paper prior to using these sheets.

## Document Control
RD.045 MoSCoW List |  |  |  |  | <Document Reference Number>
2019-11-07 18:43
Document Control
Change Record
| Date | Author | Version | Change Reference
| 2010-01-01 | <Author> | 0.1
Reviewers
| No | Name | Position | Note

## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
1 | US.101 | 1 | Problem Statement | Everyone | 2019-11-01 16:00 | 2019-11-01 17:00 | 0 | Completed | 1 Hrs | Better understanding of problem statement and the requirements
|  | 2 | Facilities | Everyone | 2019-11-01 17:00 | 2019-11-01 18:00 | 0 | Completed | 1 Hrs | Disscussion of requirements was done
|  | 3 | Forming Teams | Everyone | 2019-11-01 18:00 | 2019-11-01 18:30 | 0 | Completed | 0.5 Hrs | Roles were distributed according to the discussion done between team members
1 | US.102 | 1 | Deciding Tables | Everyone | 2019-11-02 09:00 | 2019-11-02 10:30 | 0 | Completed | 1 Hr | Tables Decided
|  | 2 | Table Properties | Everyone | 2019-11-02 11:00 | 2019-11-02 12:30 | 0 | Completed | 2 Hrs | Disscussion done
|  | 3 | Database | Team A | 2019-11-02 14:00 | 2019-11-02 15:30 | 1 | Completed | 1.5 Hrs | Tables Created
2 | US.201 | 1 | Web API Models | Team A | 2019-11-02 16:30 | 2019-11-02 18:00 | 0 | Completed | 1 Hr | Models Created
|  | 2 | Stored Procedures | Team A | 2019-11-04 09:00 | 2019-11-04 10:00 | 1 | Completed | 2 Hr | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team A | 2019-11-04 11:30 | 2019-11-04 13:00 | 0 | Completed | 1.5 Hrs | Controller was linked to the database
|  | 4 | MVC Models | Team A | 2019-11-04 14:00 | 2019-11-04 14:30 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 5 | MVC Controller | Team A | 2019-11-04 14:30 | 2019-11-04 16:00 | 0 | Completed | 1 Hr | Views were created and linked to the methods in Controller
|  | 6 | MVC Views | Team A | 2019-11-04 16:30 | 2019-11-04 18:30 | 0.5 | Completed | 2 Hrs | All the views were tested properly. Error
|  | 7 | Validation and Testing | Team A | 2019-11-05 09:00 | 2019-11-05 10:00 | 0 | Completed | 1 Hr | All the views were tested properly
|  | 8 | Final Changes | Team A | 2019-11-05 10:00 | 2019-11-05 10:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
2 | US.202 | 1 | Web API Models | Team C | 2019-11-02 16:30 | 2019-11-02 18:00 | 0 | Completed | 1 Hr | Models Created
|  | 2 | Stored Procedures | Team B | 2019-11-04 09:00 | 2019-11-04 10:00 | 1 | Completed | 2 Hr | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team B | 2019-11-04 11:30 | 2019-11-04 13:00 | 0 | Completed | 1.5 Hrs | Controller was linked to the database
|  | 4 | MVC Models | Team C | 2019-11-04 14:00 | 2019-11-04 14:30 | 0 | Completed | 0.5 Hrs | Models were created along with Validation
|  | 5 | MVC Controller | Team B | 2019-11-04 14:30 | 2019-11-04 16:00 | 0 | Completed | 1 Hr | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team B and C | 2019-11-04 16:30 | 2019-11-04 18:30 | 0.5 | Completed | 2 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team B and C | 2019-11-05 09:00 | 2019-11-05 10:00 | 0 | Completed | 1 Hr | All the views were tested properly
|  | 8 | Final Changes | Team B | 2019-11-05 10:00 | 2019-11-05 10:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
2 | US:203 | 1 | MVC Views | Team A | 2019-11-05 11:00 | 2019-11-05 12:00 | 0 | Completed | 1 Hr | View was created
2 | US:204 | 1 | MVC Views | Team B and C | 2019-11-05 12:00 | 2019-11-05 13:00 | 0 | Completed | 1 Hr | View was created
3 | US.301 | 1 | Web API Models | Team A | 2019-11-05 14:00 | 2019-11-05 14:30 | 0 | Completed | 0.5 Hrs | Models Created
|  | 2 | Stored Procedures | Team A | 2019-11-05 14:30 | 2019-11-05 15:30 | 0 | Completed | 0.5 Hrs | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team A | 2019-11-05 15:30 | 2019-11-05 16:30 | 0 | Completed | 1 Hr | Controller was linked to the database
|  | 4 | MVC Models | Team A | 2019-11-05 17:00 | 2019-11-05 17:30 | 0 | Completed | 0.5 Hrs | Models were created along with Validation
|  | 5 | MVC Controller | Team A | 2019-11-05 17:30 | 2019-11-05 18:00 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team A | 2019-11-05 18:00 | 2019-11-05 18:30 | 0.5 | Completed | 1 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team A | 2019-11-05 19:00 | 2019-11-05 19:30 | 0 | Completed | 0.5 Hrs | All the views were tested properly
|  | 8 | Final Changes | Team A | 2019-11-05 19:30 | 2019-11-05 20:00 | 0 | Completed | 0.5 Hrs | Final Changes were made
3 | US.302 | 1 | Web API Models | Team B | 2019-11-05 14:00 | 2019-11-05 14:30 | 0 | Completed | 0.5 Hrs | Models Created
|  | 2 | Stored Procedures | Team B | 2019-11-05 14:30 | 2019-11-05 15:30 | 0 | Completed | 0.5 Hrs | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team B | 2019-11-05 15:30 | 2019-11-05 16:30 | 0 | Completed | 1 Hr | Controller was linked to the database
|  | 4 | MVC Models | Team B | 2019-11-05 17:00 | 2019-11-05 17:30 | 0 | Completed | 0.5 Hrs | Models were created along with Validation
|  | 5 | MVC Controller | Team B | 2019-11-05 17:30 | 2019-11-05 18:00 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team B | 2019-11-05 18:00 | 2019-11-05 18:30 | 0 | Completed | 0.5 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team B and C | 2019-11-05 18:30 | 2019-11-05 19:00 | 0 | Completed | 0.5 Hrs | All the views were tested properly
|  | 8 | Final Changes | Team B | 2019-11-05 19:00 | 2019-11-05 19:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
3 | US.303 | 1 | Web API Models | Team A | 2019-11-06 09:00 | 2019-11-06 10:00 | 0 | Completed | 1 Hr | Models Created
|  | 2 | Stored Procedures | Team A | 2019-11-06 10:00 | 2019-11-06 11:00 | 0 | Completed | 0.5 Hrs | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team A | 2019-11-06 11:00 | 2019-11-06 12:00 | 0 | Completed | 0.5 Hrs | Controller was linked to the database
|  | 4 | MVC Models | Team A | 2019-11-06 14:00 | 2019-11-06 15:00 | 0 | Completed | 1 Hr | Models were created along with Validation
|  | 5 | MVC Controller | Team A | 2019-11-06 15:00 | 2019-11-06 16:00 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team A | 2019-11-06 16:30 | 2019-11-06 17:00 | 0 | Completed | 0.5 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team A | 2019-11-06 17:30 | 2019-11-06 18:00 | 0 | Completed | 0.5 Hrs | All the views were tested properly
|  | 8 | Final Changes | Team A | 2019-11-06 18:00 | 2019-11-06 18:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
3 | US.304 | 1 | Web API Models | Team C | 2019-11-05 14:00 | 2019-11-05 14:30 | 0 | Completed | 0.5 Hrs | Models Created
|  | 2 | Stored Procedures | Team C | 2019-11-05 14:30 | 2019-11-05 15:30 | 0 | Completed | 1 Hr | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team C | 2019-11-05 15:30 | 2019-11-05 16:30 | 0 | Completed | 1 Hr | Controller was linked to the database
|  | 4 | MVC Models | Team C | 2019-11-05 17:00 | 2019-11-05 17:30 | 0 | Completed | 0.5 Hrs | Models were created along with Validation
|  | 5 | MVC Controller | Team C | 2019-11-05 17:30 | 2019-11-05 18:00 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team C | 2019-11-05 18:00 | 2019-11-05 18:30 | 0 | Completed | 0.5 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team B and C | 2019-11-05 18:30 | 2019-11-05 19:00 | 0 | Completed | 0.5 Hrs | All the views were tested properly
|  | 8 | Final Changes | Team B | 2019-11-05 19:00 | 2019-11-05 19:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
3 | US.305 | 1 | Web API Models | Team A | 2019-11-07 09:00 | 2019-11-07 10:00 | 0 | Completed | 1 Hr | Models Created
|  | 2 | Stored Procedures | Team A | 2019-11-07 10:00 | 2019-11-07 11:00 | 0 | Completed | 0.5 Hrs | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team B and C | 2019-11-07 11:00 | 2019-11-07 12:00 | 0 | Completed | 0.5 Hrs | Controller was linked to the database
|  | 4 | MVC Models | Team A | 2019-11-07 14:00 | 2019-11-07 15:00 | 0 | Completed | 1 Hr | Models were created along with Validation
|  | 5 | MVC Controller | Team A | 2019-11-07 15:00 | 2019-11-07 16:00 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team A | 2019-11-07 16:30 | 2019-11-07 17:00 | 0 | Completed | 0.5 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team A and B | 2019-11-07 17:30 | 2019-11-07 18:00 | 0 | Completed | 0.5 Hrs | All the views were tested properly
|  | 8 | Final Changes | Team A | 2019-11-07 18:00 | 2019-11-07 18:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
3 | US.306 | 1 | Web API Models | Team C | 2019-11-06 09:00 | 2019-11-06 10:00 | 0 | Completed | 1 Hr | Models Created
|  | 2 | Stored Procedures | Team B | 2019-11-06 10:00 | 2019-11-06 11:00 | 0 | Completed | 0.5 Hrs | Required Stored procedures were discussed and created
|  | 3 | Web API Controller | Team B | 2019-11-06 11:00 | 2019-11-06 12:00 | 0 | Completed | 0.5 Hrs | Controller was linked to the database
|  | 4 | MVC Models | Team C | 2019-11-06 14:00 | 2019-11-06 15:00 | 0 | Completed | 1 Hr | Models were created along with Validation
|  | 5 | MVC Controller | Team B | 2019-11-06 15:00 | 2019-11-06 16:00 | 0 | Completed | 0.5 Hrs | WebApi was Consumed in Controller
|  | 6 | MVC Views | Team B and C | 2019-11-06 16:30 | 2019-11-06 17:00 | 0 | Completed | 0.5 Hrs | Views were created and linked to the methods in Controller
|  | 7 | Validation and Testing | Team B and C | 2019-11-06 17:30 | 2019-11-06 18:00 | 0 | Completed | 0.5 Hrs | All the views were tested properly
|  | 8 | Final Changes | Team B | 2019-11-06 18:00 | 2019-11-06 18:30 | 0 | Completed | 0.5 Hrs | Final Changes were made
4 | US:401 | 1 | Presentation Slides | Team C | 2019-11-07 14:00 | 2019-11-05 18:00 | 0 | Completed | 2.5 Hrs | Presentation was made
4 | US:402 | 1 | Overall Testing | Team B | 2019-11-07 14:00 | 2019-11-05 18:00 | 0 | Completed | 3 Hr | Testig and final changes
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Product Backlog (Scrum)
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact
Sprint 1
1 | Problem Statement | Must | US:101 | Online Banking System | Client | Everyone | Average | M
2 | Database | Must | US:102 | Table Creation | Client | Everyone | Complex | H
Sprint 2
1 | Home Page | Should | US:201 | Register | Client | Team A and B | Complex | M
2 | Home Page | Must | US:202 | Login | Client | Team C | Complex | M
3 | Home Page | Could | US:203 | About | Developer | Team A | Very Simple | L
4 | Home Page | Could | US:204 | Contact | Developer | Team B and C | Very Simple | L
Sprint 3
1 | User Account | Must | US:301 | Account Details | Client | Team A | Simple | L
2 | User Account | Must | US:302 | Payee | Client | Team B | Complex | M
3 | User Account | Must | US:303 | Transactions | Client | Team A | Complex | M
4 | User Account | Must | US:304 | Cheque Book Request | Client | Team C | Simple | L
5 | User Account | Must | US:305 | Loan | Client | Team A | Complex | M
6 | User Account | Must | US:306 | Change Password | Client | Team B and C | Simple | M
Sprint 4
1 | Presentation | Could | US:401 | Slides | Developer | Team C | Very Simple | L
2 | Demo | Could | US:402 | Overall Testing | Developer | Team B and A | Very Simple | L
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.